## Actions Status
Actions
MSP Benefits Management Vs Program Management Flow
Program Flow
Identify Program (goals, scope, stakeholders…)
Define Program
Managing the tranches (execution of projects, building the capabilities)
Deliver the capabilities (completion of projects)
Close program
Benefits Flow
Initial assessment of how benefits will be delivered
Define Benefits management strategy, practices and governance
Review, conduct, assess benefits and align program to strategic change
Ensure benefits realization is done and communicated
Colour convention
Done
Receiver
Planned
ongoing
Delayed
At risk
RESPONSIBLES

## Benefits-Profile
Benefit profile
Objective | Benefit name
Organizational goal | Metric/goal which this benefit contributes to
Description | of the outcome (benefit) to be achieved
Outcome Category | as per value map of the outcomes
Included in business case? | Yes / No
Tracked status? (date) | Yes / No (dd/mm/yyyy)
Benefit Type | Financial Status | Financial / non-financial Financial: specific amount. Non-financial: specify indirect impact
| Continuity Status | Lasting / Increasing / Once-Off Lasting: a benefit that is achieved early and continues (i.e.: software licence no longer required). Increasing benefit: A benefit that develops further over time (i.e.: adoption of new capabilities). Once-Off: it only occurs once (i.e.: one-off cost saving)
| # | Measurement description | Baseline Measure | Target Measure | Target Start Date | Frequency | Target End Date
Measurement | 1 | Description of measurement | The current state | The target state | dd/mm/yyy | how often? | dd/mm/yyy
2
3

## Benefits Report
Benefits report
Project Name | acme project |  |  | Reporting period | Week / date
Version | 2.0 |  |  | Prepared by | Name Surname
Outcome ID | Outcome description | Measure Name | Variance | Explanation | Action
Proj.015-01 | Outcome description | Total Cost of Ownership | -50000
Proj.015-02 | Time to deliver…
Proj.015-03 | Clear communication | Weekly report to all BPOs | Once a week

## Dashboard
Dashboard
Financial | Customer Service
Overall rating: yellow | Overall rating: red
Operating expenditure aligned with budget | % satis
Positive cashflow every single month
Internal Processes
Overall rating: yellow | Overall rating: green

## RACI
Legend R - Responsible (Those that get the job done) A - Accountable (Those providing approval or final review) C - Consulted (Required to consult) I - Informed (Optional to consult, required to inform) | Sponsor group | SRO | Business Managers | Other Stakeholders | Programme Manager | BCM | PMO | Comments / Status
Overall
Reports to the sponsoring group the delivery of the program benefits | A | R
Ensure the program and business areas keeps focus on the benefits delivery
Benefits management strategy: created, adjusted, improved and enforced |  | A |  | C | R | C
Benefits management strategy: develop it |  | A |  | C | R | C
Identification & planning
Identify and quantify benefits |  |  | C | C | C | R
Develop and maintain business benefits profiles |  |  | C |  |  | R
Deliver a particular benefit as profiled | [5 empty] | R
Ensure there is not double counting of benefits | [5 empty] | R
Develop benefits realization plan |  | A |  | C | R | C
Execution & review
Ensure the delivery of the capability is aligned to maximize realization of benefits |  | A |  |  | R
Gather information for the benefits reviews |  |  |  |  | A |  | R
Produce performance reports |  |  |  |  | A |  | R
Monitor the progress of benefit realization plan |  |  |  |  | A |  | R
Maintains benefits information under change control process |  |  |  |  | A |  | R
Benefit review during the program |  | A |  |  | R | C
Benefit review after the program |  | A |  |  |  | R
Internal audits |  | A |  |  | R

## Benefits-Category
Category | Values
Value | Economic | effectiveness | effectivity
Finance | cashable | non-cashable
Corporate | Flexibility | Compliance | Enhanced quality | Strategic fit | Stakeholder Impact
Timeline | short term | long term
Level of risk | Low level | Medium Level | High level